## #O1 Sprint Goals
Product Goal | Launch a food ordering mobile app that is able to compete with Talabat
Sprint Goals
1 | Create basic mobile app structure
2 | Allow users to create profiles
3 | List restaurants, products details, and menus
4 | Build capability to add & purchase food using a credit card
5 | Develop a platform for restaurants to manage orders

## #O2 Sprint Tasks
ID | User Story | Tasks | Assignee | Total Estimated Hours | Completion Date | Status
1 | As a new user, I want to create a new account so that I can be able to save my information and start ordering food | Place suitable sign up text boxes and fields | Maha | 30 | 2022-11-01 | Completed
|  | Direct the app input to a DB | Manal |  |  | Completed
2 | As a customer, I want to browse restaurants so that I can choose what food to order from a variety of options | Add restaurants | Maha | 45 | 2022-11-15 | Completed
|  | Use cookies to customize user recommendations | Maha |  |  | Completed
3 | As a customer, I want to search for restaurants on the app so that I can check if restaurants of my choice exist | Place a search bar that renders satisfactory results | Maha | 25 | 2022-11-20 | Completed
4 | As a customer, I want to view the menu so that I can see available food options, pictures, and their relative prices | Ask restaurants to add their menus | Restaurants | 35 | 2022-11-30 | Completed
|  | Verify the input is accurate | Hind |  |  | Completed
5 | As a customer, I want to add to cart so that I can view the total quantity and price and then order | Create functions that aggregate prices | Maha | 20 | 2022-12-02 | Completed
6 | As a customer, I want to purchase so that I can get my food delivered | Set up a secure channel for credit card purchases | Manal | 55 | 2022-12-18 | Completed
|  | Automate order confirmation emails | Manal |  |  | Completed
7 | As a restaurant staff, I want to view orders so that I can prepare them correctly | Send an alarming notification to restaurant device | Manal | 20 | 2022-12-21 | Completed
8 | As a restaurant staff, I want to mark orders as delivered so that I close open orders and document the status | Place an order fulfillment button on the platform | Maha | 20 | 2022-12-24 | Completed

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
1 | Create Account | As a new user, I want to create a new account so that I can be able to save my information and start ordering food | 4 | Medium | 1 | Completed
2 | View Restaurants | As a customer, I want to browse restaurants so that I can choose what food to order from a variety of options | 3 | Low | 2 | Completed
3 | Search Restaurants | As a customer, I want to search for restaurants on the app so that I can check if restaurants of my choice exist | 5 | High | 2 | Completed
4 | View Menu | As a customer, I want to view the menu so that I can see available food options, pictures, and their relative prices | 5 | High | 3 | Completed
5 | Add to Cart | As a customer, I want to add to cart so that I can view the total quantity and price and then order | 5 | High | 3 | Completed
6 | Purchase | As a customer, I want to purchase so that I can get my food delivered | 5 | High | 4 | Completed
7 | Restaurant views order | As a restaurant staff, I want to view orders so that I can prepare them correctly | 5 | High | 5 | Completed
8 | Restaurant marks order as delivered | As a restaurant staff, I want to mark orders as delivered so that I close open orders and document the status | 2 | Low | 5 | Completed